AGENCY ENABLEMENT PACK

Social Media Client
Onboarding Workbook

A practical packet for intake, kickoff, access, approvals, measurement, handoff, and offboarding.

Purpose: Turn a sales handoff into a workable client operating system. Keep strategy, source material, access, approvals, and reporting aligned from day one.

| Prepared for | Enter client / brand | Agency lead | Enter name |
| --- | --- | --- | --- |
| Kickoff date | Enter date | First publish target | Enter date |

Designed for agencies managing one client or an entire roster. Product-neutral, permission-safe, and ready to adapt to the client contract.

# 1. How to use this workbook

Use this page: Complete the short intake first. Use the workshop for decisions that require discussion. Do not send a 70-question form and call it onboarding.

## Four steps

- Collect the essentials needed to schedule the workshop.

- Run the agency-led workshop and make the choices together.

- Request access and source material only after scope and ownership are clear.

- Record the operating agreement, test the workflow, and close open items before production starts.

## First-pass intake

| Client / brand | Enter legal name and public-facing brand name |
| --- | --- |
| Website | Enter primary website and any campaign landing page |
| Main contact | Name, role, email, time zone |
| Decision maker | Name and role |
| Day-to-day approver | Name, role, backup |
| Agency lead | Name, role, backup |
| Contract start | Enter date |
| First publish target | Enter date |

Stop condition: If nobody can name the final approver, the first content deadline is not ready to be promised.

# 2. Essential client intake

Use this page: Keep this short enough that a client will complete it. Resolve ambiguity in the workshop rather than adding more fields.

## Business and campaign context

| Primary offer | What can the audience buy, book, visit, join, or believe? |
| --- | --- |
| Priority audience | Who matters most during the first 30 days? |
| Key dates | Launches, events, promotions, closures, embargoes |
| No-go topics | Claims, subjects, competitors, visuals, or language to avoid |

## Choose the primary job of organic social

- Maintain trust and visible proof that the company is active.

- Support sales with current proof, expertise, and shareable assets.

- Capture demand through profile actions and tracked routes to offers.

- Support recruiting and employer credibility.

- Route customer questions to the right owner.

- Supply message and creative concepts that paid media can test.

| Channels in scope | List only contracted channels |
| --- | --- |
| Channels out of scope | Name exclusions to prevent silent expansion |
| Cadence and formats | Posts, carousels, short video, stories, articles |
| Other owners | Community, paid media, influencers, PR, recruiting |

# 3. Agency-led onboarding workshop

Use this page: Use the session to make decisions, not to read the intake form aloud. Recommended working time: 75 minutes.

| Time | Working block | Output |
| --- | --- | --- |
| 0-10 min | Context and constraints | Confirm scope, dates, stakeholders, and anything that can block launch. |
| 10-25 min | Business goal and social role | Choose the primary and secondary job of organic social. |
| 25-40 min | Audience and proof | Define what the audience should believe, why, and which evidence supports it. |
| 40-55 min | Content system | Agree themes, formats, sources, recurring series, and exclusions. |
| 55-67 min | Approval and communication | Name owners, review windows, escalation, and the source of truth. |
| 67-75 min | First 30 days | Confirm decisions, owners, deadlines, and the first publish gate. |

## Workshop prompts

- What should a qualified prospect understand after seeing three posts?

- Which proof can we publish without waiting for a new case study?

- What would make a post risky, off-brand, or misleading?

- Where does organic social hand off to sales, service, recruiting, paid, or PR?

- Which decision must be made today to protect the first publish date?

Decisions made in the workshop

Enter notes

# 4. Goal-to-measurement map

Use this page: For many brands, organic social is better treated as trust and activity infrastructure than as a guaranteed reach engine. Reach and follower growth are useful diagnostics, not automatic business outcomes.

| Organic social role | Practical job | Measures to watch | Guardrail |
| --- | --- | --- | --- |
| Trust and active presence | Show current expertise, offers, people, proof, and signs of life. | Publishing reliability; profile completeness; stakeholder feedback | Keep content current and credible. |
| Sales enablement | Give sales teams useful proof and shareable explanations. | Asset adoption; tracked profile clicks; assisted conversations | Agree CRM or UTM limits before reporting. |
| Demand capture | Create clear routes from profiles and posts to relevant offers. | Profile actions; landing-page sessions; assisted conversions | Do not claim last-click causation without evidence. |
| Customer care | Route recurring questions and service issues to an accountable owner. | Ownership coverage; handoff time; repeated question themes | Only if community management is in scope. |
| Recruiting | Build employer proof for candidates and employees. | Careers-page actions; qualified applicants; employee participation | Coordinate with recruiting. |
| Paid creative support | Build a reusable message and creative concept library. | Concepts produced; reuse rate; paid-test learning | Paid results belong to the paid owner. |
| Relationship building | Stay visible with partners, customers, peers, and target accounts. | Qualified interactions; partner participation; direct feedback | Favor relevance over raw engagement. |

| Primary role | Choose one |
| --- | --- |
| Secondary role | Choose one |
| Measurement owner | Name and system |

# 5. Access matrix

Use this page: Request role-based access. Never ask a client to email passwords, recovery codes, or shared administrator credentials.

| System | Client owner | Permission path | Agency needs | Verified |
| --- | --- | --- | --- | --- |
| Meta Business Portfolio | Client | Partner access or assigned Page / Instagram assets | Content or admin as scoped |  |
| LinkedIn | Client | Page role; Campaign Manager only if paid is in scope | Content admin or scoped role |  |
| X | Client | Delegate access; Ads access only if paid is in scope | Contributor or scoped role |  |
| TikTok Business Center | Client | Partner/member assignment | Content or advertiser as scoped |  |
| YouTube | Client | Channel permissions through Brand Account / Studio | Editor or scoped role |  |
| Pinterest Business | Client | Business access; ads only if scoped | Employee / partner role |  |
| Google Business Profile | Client | Manager access | Manager if local posting is scoped |  |
| GA4 | Client | Property access | Viewer or analyst |  |
| Google Tag Manager | Client | Container access | Read or edit only if tracking is scoped |  |
| Search Console | Client | Property access | Restricted or full as needed |  |
| Social production / scheduler | Agreed owner | Workspace invitation | Role matching contract |  |
| Shared asset folder | Client | Named folder or DAM collection | View or contribute |  |
| CRM | Client | Report/dashboard access only when required | Least privilege |  |

Verification: Test access while the client is present when possible. Record who granted it, the role, the date, and any expiry.

# 6. Source pack

Use this page: Every recurring claim, offer, visual, and brand rule needs a source of truth. Ask for links and owners, not a pile of unlabeled attachments.

| Source group | Required material | Owner | Link / status |
| --- | --- | --- | --- |
| Brand foundation | Voice, audience, positioning, terms, prohibited language |  |  |
| Visual identity | Current logos, colors, fonts, templates, image rules |  |  |
| Approved examples | Posts, ads, sales material, or pages that sound right |  |  |
| Offers and pricing | Current product/service details, qualifiers, dates |  |  |
| Proof and claims | Evidence, research, product documentation, approved language |  |  |
| Customer proof | Testimonials, case studies, permissions, release status |  |  |
| Rights and licenses | Photo, video, music, creator, employee, and location rights |  |  |
| Campaign calendar | Launches, events, promotions, blackout dates, embargoes |  |  |
| Content history | Recent posts, reports, lessons, repeated objections |  |  |
| Policies | Legal, privacy, accessibility, industry, crisis, security |  |  |
| Reporting baseline | Current KPIs, dashboards, attribution limits, definitions |  |  |

| Canonical source location | Folder, DAM, knowledge base, or portal |
| --- | --- |
| Source-pack owner | Name and backup |
| Review / expiry cadence | When must facts, offers, and rights be rechecked? |

# 7. Welcome checklist

Use this page: Use this as the account lead's pre-kickoff gate. Items that do not apply should be marked N/A with a reason.

| Welcome item | Owner | Due | Status |
| --- | --- | --- | --- |
| Contract and scope available to delivery team | Agency lead |  |  |
| Welcome email sent with named contacts | Account lead |  |  |
| Client portal or shared workspace created | Operations |  |  |
| Essential intake returned | Client |  |  |
| Agency-led workshop booked | Account lead |  |  |
| Source-pack request sent | Strategist |  |  |
| Access requests mapped to scope | Operations |  |  |
| Approver and backup identified | Client |  |  |
| Communication channel and cadence agreed | Both |  |  |
| First content milestone scheduled | Production lead |  |  |
| Reporting baseline and owner identified | Reporting lead |  |  |
| Known risks and escalation owner logged | Account lead |  |  |

## What the client receives

- Named agency team and clear responsibilities.

- Kickoff agenda and preparation request.

- Access instructions based on least privilege.

- First 30-day plan with dates and decision gates.

- Approval and communication agreement for sign-off.

# 8. Kickoff agenda

Use this page: The kickoff confirms how the engagement will run. The workshop produces the strategic and operational decisions.

| Minutes | Topic | Lead | Decision / output |
| --- | --- | --- | --- |
| 0-5 | Introductions and decision authority | Everyone | Named owner and approver |
| 5-15 | Scope, exclusions, dates, dependencies | Agency lead | Confirmed boundary |
| 15-28 | Organic social role and goal map | Strategist | Primary role and measures |
| 28-38 | Source pack and access | Operations | Owners and due dates |
| 38-48 | Content, approval, and escalation | Production lead | Recorded workflow |
| 48-56 | First 30-day plan | Account lead | Decision gates |
| 56-60 | Read back decisions and next actions | Agency lead | No ambiguous owners |

## Decision log

| Decision | Owner | Due | Where recorded |
| --- | --- | --- | --- |

Close: End by reading back every owner and date. Send the written decision log after the meeting.

# 9. First 30 days

Use this page: The first month should prove the operating system before the agency scales volume.

| Window | Agency output | Client input | Exit check |
| --- | --- | --- | --- |
| Days 0-3 | Confirm scope, goals, approvers, source pack, and access requests. | Return intake; assign owners; grant safe access. | No unnamed approver or critical source gap. |
| Days 4-10 | Build brand/content framework; draft themes; prepare sample set. | Review assumptions and high-risk claims. | Strategy and factual basis accepted. |
| Days 11-20 | Produce first batch; run accessibility, rights, and evidence checks. | Review through agreed workflow. | Approval test completed and conditions logged. |
| Days 21-30 | Publish/schedule; validate tracking; document lessons; prepare baseline report. | Confirm measurement notes and next cycle. | Repeatable monthly workflow ready. |

## Decision gates

- Gate 1: Scope, owners, and access path are confirmed.

- Gate 2: Brand and content assumptions are accepted.

- Gate 3: The approval path works with a real sample.

- Gate 4: Publishing and reporting definitions are documented.

Risks or dependencies that can move the first publish date

Enter notes

# 10. Approval agreement

Use this page: Record who reviews, who decides, what must travel with an asset, and what happens when a deadline is missed.

| Agency reviewer | Name, role, backup |
| --- | --- |
| Client approver | Name, role, backup |
| Specialist reviewers | Legal, compliance, product, HR, privacy, accessibility |
| Standard review window | Business hours or days |
| High-risk review window | Client policy or named SLA |
| Approval system | Where the final decision is recorded |

## Workflow rules

- One named approver records the final decision.

- Claims, sources, rights, and accessibility status travel with the asset.

- Conditional approval names the required change and verification owner.

- Silence is not approval. Missed deadlines follow the escalation path.

- A material change to claim, offer, asset, date, or context reopens review.

- Emergency publishing follows the client's incident plan.

Approval exceptions and regulated-content requirements

Enter notes

# 11. Communication agreement

Use this page: Separate discussion from decisions. Use one documented source of truth for tasks, approvals, source material, and reporting.

| Event | Channel / system | Owner | Expected response |
| --- | --- | --- | --- |
| Routine questions |  |  |  |
| Content discussion |  |  |  |
| Final approvals |  |  |  |
| Urgent escalation |  |  |  |
| Source material |  |  |  |
| Reports and decisions |  |  |  |

| Meeting cadence | Weekly, biweekly, monthly, QBR |
| --- | --- |
| Primary time zone | Include working hours |
| Escalation ladder | Name, channel, when to use |
| Decision-log owner | Who sends and maintains the record? |

## Communication guardrails

- Do not treat a direct message or verbal comment as final approval unless it is logged.

- Consolidate conflicting feedback before returning it to production.

- Label urgent work by consequence, not by who asked loudest.

# 12. Definition of complete and internal handoff

Use this page: Onboarding is complete when the team can produce, review, publish, and report without relying on unwritten context.

## Definition of complete

- Contract scope and exclusions are available to delivery.

- Primary and secondary organic social roles are recorded.

- Goals, measures, ownership, and attribution limits are recorded.

- Source pack has canonical links, owners, and review dates.

- Role-based access is verified without shared passwords.

- A real content sample has passed the approval workflow.

- Communication, escalation, and decision-log systems are agreed.

- The first 30-day plan has owners, dates, and decision gates.

- Open risks are accepted, assigned, or blocking launch.

## Internal handoff

| Team | Handoff package | Owner | Done |
| --- | --- | --- | --- |
| Sales / partnerships | Scope, promises, commercial context, unresolved expectations |  |  |
| Account lead | Contacts, cadence, risks, escalation, decision log |  |  |
| Strategy | Social role, audience, themes, proof, measurement map |  |  |
| Production | Sources, templates, content rules, deadlines, review path |  |  |
| Reporting | Baseline, definitions, links, attribution limits, cadence |  |  |
| Paid / community / PR | Handoffs and exclusions where these functions intersect |  |  |

# 13. Offboarding and access removal

Use this page: Plan offboarding during onboarding. The client should retain ownership, continuity, and a clear record of what changes when the engagement ends.

| Offboarding action | Owner | Due | Complete |
| --- | --- | --- | --- |
| Confirm end date, final scope, and transition owner | Both |  |  |
| Export approved content, calendars, reports, and decision history | Agency |  |  |
| Return or transfer editable assets and source files | Agency |  |  |
| Document scheduled posts and publishing dependencies | Agency |  |  |
| Remove agency users, partners, tokens, and integrations | Client / agency |  |  |
| Rotate any credentials exposed outside role-based access | Client |  |  |
| Confirm data retention, deletion, and archive obligations | Both |  |  |
| Deliver final measurement notes and known attribution limits | Agency |  |  |
| Record outstanding rights, claims, expiries, or compliance issues | Agency |  |  |
| Obtain written completion acknowledgment | Both |  |  |

## Access and asset register

| System / asset | Final owner | Agency removed | Export / archive location |
| --- | --- | --- | --- |

Final check: Do not close the account until the client can find the source files, see what is scheduled, and confirm that agency access has been removed.